## Slide 1
SOLUTION PROPOSAL • DIGITAL EXPERIENCE MIGRATION
Pharma Brand Portfolio Migration to
Adobe Experience Manager – Edge Delivery Services
Six brand sites — Lupron, Lupron Ped, Armour Thyroid, Hypothyroid Hub, LILETTA & LILETTA HCP
Block inventory · Design system · Integrations · Migration approach · Effort & roadmap
Prepared by Cognizant • Confidential

## Slide 2
AT A GLANCE
Executive Summary
A single, content-driven re-platform of six AbbVie brand sites onto Adobe Edge Delivery Services — built on one shared design system and block library, delivered through a proven 6-stage lifecycle.
6
brand sites in scope
1
shared design system & block library
16
existing blocks reused
~190
person-days (165–215 range)
Why this matters
Performance & SEO — EDS targets a 100 Lighthouse score; replaces legacy jQuery/Bootstrap and an Angular SPA with fast, static-first delivery.
Authoring agility — marketers edit in documents; no code release for content change, accelerating regulated-content updates.
Compliance by design — ISI / PI fair-balance, references and PRC/job codes treated as first-class migration artifacts.
Economies of scale — build common blocks once, theme per brand; later sites get faster and cheaper.
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
2

## Slide 3
SCOPE
Portfolio at a Glance
Site
Audience
Therapeutic area
Source state
Complexity
lupron.com
Patient (multi-indication)
Prostate / endo / fibroids
Live HTML
Med–High
lupronpedpro.com
Caregiver / HCP
Central precocious puberty
WAF-blocked
Low–Med
armourthyroid.com
Patient
Hypothyroidism
Angular SPA
Medium
hypothyroidhub.com
HCP portal
Hypothyroidism
WAF-blocked
Med *
liletta.com
Patient
Contraception (IUD)
Live HTML
High
lilettahcp.com
HCP
Contraception (IUD)
Live HTML
Med–High
* Highest discovery risk — site is WAF-blocked and scope (HCP portal / registration / interactive tools) is unconfirmed. A discovery spike precedes its estimate.
All six are AbbVie properties sharing a common technology stack (Adobe Launch, OneTrust, Bootstrap/jQuery, Adobe Typekit) — the basis for one shared design system.
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
3

## Slide 4
METHOD
Our Solution Approach
AEM Edge Delivery Services — vanilla JS/CSS, no build step, three-phase loading, document-authored content.
One shared design system
Single AbbVie brand base; per-brand theming via token overrides — not bespoke code.
Colors, type, spacing & motion captured once as reusable tokens.
One block library
16 existing blocks reused (gate, ISI bar, hero, cards, tabs…).
7 new shared blocks built once; 9 site-specific blocks where needed.
Content-driven delivery
Every block starts from a block.md content-model contract.
Authored draft content drives decoration & automated tests.
Compliance-first
ISI/PI fair balance, references & PRC codes migrated verbatim.
WCAG 2.1 AA baked into review, not bolted on.
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
4

## Slide 5
HOW WE BUILD
The 6-Stage EDS Delivery Lifecycle
Each block flows through six specialised delivery stages — a repeatable, quality-gated lifecycle.
STAGE 1
Strategist
Story, acceptance criteria, content model (block.md), IA
STAGE 2
Styleforge
Design tokens, color/type, responsive & motion specs
STAGE 3
Blockwright
Build block JS/CSS/markup, draft content, lint, local tests
STAGE 4
Sentinel
Code review (standards + WCAG AA), Playwright specs, green run
STAGE 5
Composer
Block-library entry + page assembly from authored content
STAGE 6
Pilot
Pre-push hygiene, PageSpeed ≥100, preview URL, PR prep
Plan → Design → Build → Review/Test → Integrate → Deploy
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
5

## Slide 6
REUSE STRATEGY
Shared Block Library
Reuse first, build once, reuse again — the library compounds across the portfolio.
Reused (existing)
16 blocks — 0 build cost
audience-gate, isi-bar
header, footer, navigation
hero-carousel, nav-cards, tabs
stat-bar, split-section
promo-banner, promo-pair, resource-list
New — shared
7 blocks — built once
savings-card
faq-accordion
reference-list
downloadable-resource
dosing-table, discussion-guide, spec-list
New — site-specific
9 blocks — cost drivers
indication-selector (lupron)
quiz, comparison-table, email-share (liletta)
clinical-data-table, rep-request-form, video-embed (HCP)
symptom-checker (hub), symptom-checklist (ped)
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
6

## Slide 7
SITE DETAIL
Per-Site Scope Summary
Site
Pages (est.)
Key new blocks
Stand-out need
lupron.com
~18
indication-selector, dosing-table
3-indication IA & dosing
lupronpedpro.com
~8
symptom-checklist, savings-card
Caregiver journey + content export
armourthyroid.com
~8
dosing-table, discussion-guide
SPA content extraction
hypothyroidhub.com
~9
symptom-checker
Scope discovery + interactive tool
liletta.com
~20
quiz, comparison-table, email-share
Most net-new + GSAP motion
lilettahcp.com
~9
clinical-data-table, rep-request-form, video-embed
Clinical data + CRM form
Interactive blocks (quiz, symptom-checker, clinical-data-table, lead forms) carry the most build, accessibility and integration effort.
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
7

## Slide 8
NON-FUNCTIONAL
Integrations, Compliance & Accessibility
Cross-cutting integrations
Analytics / tag mgmt — Adobe Experience Platform Launch/DTM (standard); GA on LILETTA HCP. Re-wired in the delayed phase.
Consent — OneTrust (Evidon on lupron, CCPA on HCP). One standardised consent pattern.
Forms → CRM — email-share & rep-request need endpoints (AbbVie / Veeva sales ops).
Video — Vimeo (HCP) via lazy facade. Fonts — Typekit + Google Fonts, self-hosted for LCP.
Savings programs — external (luprongyn, LILETTAcard, AbbVie Access) — link-out, confirm scope.
Compliance & accessibility
ISI / PI fair balance on every page — sticky ISI bar + full PI/Med Guide preserved.
References & claim substantiation — footnoted, especially on HCP clinical-data pages.
PRC / job codes (US-####) migrated verbatim and treated as locked artifacts.
WCAG 2.1 AA — gate focus-trap, keyboard ISI, accessible data tables, captioned video.
Medical-Legal-Regulatory (MLR) review runs in parallel — the key schedule driver.
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
8

## Slide 9
BOTTOM-UP SIZING
Effort Estimate
Workstream
Person-days
lupron.com
21.5
lupronpedpro.com
14.5
armourthyroid.com
14.0
hypothyroidhub.com
18.75
liletta.com
34.0
lilettahcp.com
29.0
Site subtotal
131.75
Shared foundation (build once)
27.0
Build subtotal
158.75
Program overhead (~20%): PM, QA/UAT, a11y, MLR coord.
~32.0
Grand total (point estimate)
~190
Effort by delivery stage
Blockwright (build)
38%
Sentinel (review + tests)
17%
Composer (library + pages)
16%
Strategist (plan)
12%
Styleforge (design)
9%
Pilot (deploy)
5%
Range with uncertainty: 165–215 person-days
≈ 33–43 person-weeks · ~8–10.5 person-months
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
9

## Slide 10
PHASING
Delivery Roadmap
A pod of 3 EDS engineers + tech lead + part-time PM/QA ≈ 11–14 calendar weeks (MLR in parallel).
WAVE 0
2–3 wks
Foundation
Design system, shared blocks, consent/analytics pattern, import pipeline. Validate on one pilot site.
WAVE 1
~4 wks
Lower-risk sites
lupron.com · lupronpedpro.com · armourthyroid.com — fetchable + modest interactivity.
WAVE 2
~4 wks
High-complexity
liletta.com · lilettahcp.com — most net-new interactive blocks (quiz, clinical data, forms).
WAVE 3
~2 wks
Discovery-led
hypothyroidhub.com — sequenced last; resolve scope/registration ambiguity first.
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
10

## Slide 11
PLANNING CANDOR
Risks & Assumptions
Key risks & mitigations
⚠ MLR review = #1 schedule driver
Freeze content early; lock PRC codes; parallelise sign-off.
⚠ WAF-blocked + SPA sources
Discovery spikes first; re-baseline after (3 sites).
⚠ hypothyroidhub scope unconfirmed
Scope spike before commit; could swing ±5 days.
⚠ Interactive blocks (a11y + CRM)
Early WCAG review; endpoint contracts up front.
⚠ Form endpoints (AbbVie/Veeva)
Confirm integration availability as external dependency.
Key assumptions
One shared AbbVie design system; brands differ by tokens, not bespoke blocks.
Savings/copay enrollment stays on external AbbVie properties (link-out).
Authors / migration scripts handle bulk page authoring; engineering owns blocks + assembly.
MLR/regulatory review runs in parallel and does not block engineering.
Estimates re-baselined after Wave 0 and the three discovery spikes.
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
11

## Slide 12
WHY COGNIZANT
Proven EDS lifecycle, a reusable block library, and deep regulated-pharma experience — delivering performance, compliance and speed-to-author across the whole portfolio.
1
Scope & discovery spikes
Confirm hypothyroidhub scope; export WAF-blocked & SPA content.
2
Foundation sprint (Wave 0)
Stand up design system, shared blocks & import pipeline on a pilot site.
3
Re-baseline & commit
Lock estimate and wave plan; agree MLR cadence and form/CRM dependencies.
Let’s start with a 2-week discovery sprint to lock scope and validate the foundation.
Cognizant • Confidential client proposal