## Slide 1
SOLUTION PROPOSAL • DIGITAL EXPERIENCE MIGRATION
Pharma Brand Portfolio Migration to
Adobe Experience Manager – Edge Delivery Services
Eighteen brand sites across the AbbVie portfolio — delivered in two waves
Block inventory · Design system · Integrations · Migration approach · Effort & roadmap
Prepared by Cognizant • Confidential

## Slide 2
AT A GLANCE
Executive Summary
A single, content-driven re-platform of eighteen AbbVie brand sites onto Adobe Edge Delivery Services — built on one shared design system and block library, delivered through a proven 6-stage lifecycle.
18
brand sites in scope
1
shared design system & block library
16
existing blocks reused
~409
person-days (355–465 range)
Why this matters
Performance & SEO — EDS targets a 100 Lighthouse score; replaces legacy jQuery/Bootstrap and an Angular SPA with fast, static-first delivery.
Authoring agility — marketers edit in documents; no code release for content change, accelerating regulated-content updates.
Compliance by design — ISI / PI fair-balance, references and PRC/job codes treated as first-class migration artifacts.
Economies of scale — build common blocks once, theme per brand; Wave 2’s 12 sites add almost no new blocks — near-total reuse.
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
2

## Slide 3
SCOPE
Portfolio at a Glance · Wave 1 (original six)
Site
Audience
Therapeutic area
Source state
Complexity
lupron.com
Patient (multi-indication)
Prostate / endo / fibroids
Live HTML
Med–High
lupronpedpro.com
Caregiver / HCP
Central precocious puberty
WAF-blocked
Low–Med
armourthyroid.com
Patient
Hypothyroidism
Angular SPA
Medium
hypothyroidhub.com
HCP portal
Hypothyroidism
WAF-blocked
Med *
liletta.com
Patient
Contraception (IUD)
Live HTML
High
lilettahcp.com
HCP
Contraception (IUD)
Live HTML
Med–High
* Highest discovery risk — site is WAF-blocked and scope (HCP portal / registration / interactive tools) is unconfirmed. A discovery spike precedes its estimate.
All six are AbbVie properties sharing a common technology stack (Adobe Launch, OneTrust, Bootstrap/jQuery, Adobe Typekit) — the basis for one shared design system.
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
3

## Slide 4
SCOPE
Portfolio at a Glance · Wave 2 (twelve new sites)
Site
Audience
Therapeutic area
Source state
Complexity
viberzihcp.com
HCP
IBS-D (eluxadoline)
Not fetchable
Med–High
teflaro.com
HCP
IV antibiotic
Not fetchable
Med–High
xengelstent.com
Patient
Glaucoma device (MIGS)
Not fetchable
Low–Med
myglaucoma.com
Patient (unbranded)
Glaucoma awareness
ASP.NET
Medium
restasis.com
Patient
Chronic dry eye
Not fetchable
Medium
bystolic.com
Patient
Hypertension
Server HTML
Low–Med
viibryd.com
Patient
MDD (boxed warning)
Legacy .aspx
Low–Med
infedlocator.com
HCP
IV iron locator
JS map app
Med–High
depakotehcp.com
HCP
Multi-indication (boxed)
Not fetchable
Med–High
depakote.com
Patient
Multi-indication (boxed)
Not fetchable
Med–High
taytulla.com
Patient
Oral contraceptive
Not fetchable
Medium
fetzima.com
Patient
MDD (boxed warning)
Not fetchable
Low–Med
Twelve additional AbbVie/Allergan brand sites — Wave 2 of the portfolio migration. 10 of 12 were not fetchable this pass → a discovery spike precedes each estimate.
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
4

## Slide 5
METHOD
Our Solution Approach
AEM Edge Delivery Services — vanilla JS/CSS, no build step, three-phase loading, document-authored content.
One shared design system
Single AbbVie brand base; per-brand theming via token overrides — not bespoke code.
Colors, type, spacing & motion captured once as reusable tokens.
One block library
16 existing blocks reused (gate, ISI bar, hero, cards, tabs…).
9 new shared blocks built once (incl. locator-map, risk-assessment); site-specific blocks only where the design demands — Wave 2 needs none.
Content-driven delivery
Every block starts from a block.md content-model contract.
Authored draft content drives decoration & automated tests.
Compliance-first
ISI/PI fair balance, references & PRC codes migrated verbatim.
WCAG 2.1 AA baked into review, not bolted on.
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
5

## Slide 6
HOW WE BUILD
The 6-Stage EDS Delivery Lifecycle
Each block flows through six specialised delivery stages — a repeatable, quality-gated lifecycle.
STAGE 1
Strategist
Story, acceptance criteria, content model (block.md), IA
STAGE 2
Styleforge
Design tokens, color/type, responsive & motion specs
STAGE 3
Blockwright
Build block JS/CSS/markup, draft content, lint, local tests
STAGE 4
Sentinel
Code review (standards + WCAG AA), Playwright specs, green run
STAGE 5
Composer
Block-library entry + page assembly from authored content
STAGE 6
Pilot
Pre-push hygiene, PageSpeed ≥100, preview URL, PR prep
Plan → Design → Build → Review/Test → Integrate → Deploy
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
6

## Slide 7
REUSE STRATEGY
Shared Block Library
Reuse first, build once, reuse again — the library compounds across the portfolio.
Reused (existing)
16 blocks — 0 build cost
audience-gate, isi-bar
header, footer, navigation
hero-carousel, nav-cards, tabs
stat-bar, split-section
promo-banner, promo-pair, resource-list
New — shared
9 blocks — built once
savings-card
faq-accordion
reference-list
downloadable-resource
dosing-table, discussion-guide, spec-list
locator-map *
risk-assessment *
New — site-specific
9 blocks — Wave-1 cost drivers
indication-selector (lupron)
quiz, comparison-table, email-share (liletta)
clinical-data-table, rep-request-form, video-embed (HCP)
symptom-checker (hub), symptom-checklist (ped)
Wave 2: no bespoke blocks — full reuse
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
7

## Slide 8
SITE DETAIL
Per-Site Scope Summary · Wave 1 (original six)
Site
Pages (est.)
Key new blocks
Stand-out need
lupron.com
~18
indication-selector, dosing-table
3-indication IA & dosing
lupronpedpro.com
~8
symptom-checklist, savings-card
Caregiver journey + content export
armourthyroid.com
~8
dosing-table, discussion-guide
SPA content extraction
hypothyroidhub.com
~9
symptom-checker
Scope discovery + interactive tool
liletta.com
~20
quiz, comparison-table, email-share
Most net-new + GSAP motion
lilettahcp.com
~9
clinical-data-table, rep-request-form, video-embed
Clinical data + CRM form
Interactive blocks (quiz, symptom-checker, clinical-data-table, lead forms) carry the most build, accessibility and integration effort.
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
8

## Slide 9
SITE DETAIL
Per-Site Scope · Wave 2 (twelve new sites)
Site
Pages (est.)
Key new blocks
Stand-out need
viberzihcp.com
~14
clinical-data-table, dosing-table, video-embed
HCP gate + clinical/dosing
teflaro.com
~20
dosing-table, clinical-data-table, comparison-table
Adult/peds × ABSSSI/CABP matrix
xengelstent.com
4
video-embed, locator-map *
Device DFU; low-vision a11y
myglaucoma.com
~8
risk-assessment (quiz), video-embed
Unbranded; scrapeable; quiz
restasis.com
~14
clinical-data-table, comparison-table
Multi-step savings flow
bystolic.com
~12
all shared — no bespoke block
Scrapeable; full reuse
viibryd.com
~12
all shared — no bespoke block
Boxed warning; legacy .aspx
infedlocator.com
~2
locator-map
Locator data-API dependency
depakotehcp.com
~16
indication-selector, clinical-data-table
Multi-indication; boxed
depakote.com
~16
indication-selector, dosing-table
Multi-indication; boxed
taytulla.com
~14
comparison-table, discussion-guide
Two interactive tools
fetzima.com
~14
all shared — shares viibryd
Boxed; viibryd synergy
Wave 2 introduces only two new shared blocks — locator-map and risk-assessment (*). Every other section reuses the Wave-1 library; indication-selector is reused by both Depakote sites.
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
9

## Slide 10
NON-FUNCTIONAL
Integrations, Compliance & Accessibility
Cross-cutting integrations
Analytics / tag mgmt — Adobe Experience Platform Launch/DTM (standard); GA on LILETTA HCP. Re-wired in the delayed phase.
Consent — OneTrust (Evidon on lupron, CCPA on HCP). One standardised consent pattern.
Forms → CRM — email-share & rep-request need endpoints (AbbVie / Veeva); Wave 2 adds patient savings-enrollment + an INFeD center-locator data API.
Video — Vimeo/Brightcove via lazy facade (HCP, Restasis, myGlaucoma) + a scored quiz (myGlaucoma). Fonts — Typekit + Google Fonts, self-hosted for LCP.
Savings programs — external (luprongyn, LILETTAcard, AbbVie Access) — link-out, confirm scope.
Compliance & accessibility
ISI / PI fair balance on every page — sticky ISI bar + full PI/Med Guide preserved.
References & claim substantiation — footnoted, especially on HCP clinical-data pages.
PRC / job codes (US-####) migrated verbatim and treated as locked artifacts.
WCAG 2.1 AA — gate focus-trap, keyboard ISI, accessible data tables, captioned video.
Medical-Legal-Regulatory (MLR) review runs in parallel — the key schedule driver.
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
10

## Slide 11
BOTTOM-UP SIZING
Effort Estimate · Wave 1 (original six)
Workstream
Person-days
lupron.com
21.5
lupronpedpro.com
14.5
armourthyroid.com
14.0
hypothyroidhub.com
18.75
liletta.com
34.0
lilettahcp.com
29.0
Site subtotal
131.75
Shared foundation (build once)
27.0
Build subtotal
158.75
Program overhead (~20%): PM, QA/UAT, a11y, MLR coord.
~32.0
Grand total (point estimate)
~190
Effort by delivery stage
Blockwright (build)
38%
Sentinel (review + tests)
17%
Composer (library + pages)
16%
Strategist (plan)
12%
Styleforge (design)
9%
Pilot (deploy)
5%
Range with uncertainty: 165–215 person-days
≈ 33–43 person-weeks · ~8–10.5 person-months
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
11

## Slide 12
BOTTOM-UP SIZING
Effort Estimate · Wave 2 + Program Total
Workstream
Person-days
viberzihcp.com
15.5
teflaro.com
18.5
xengelstent.com
7.5
myglaucoma.com
13.0
restasis.com
15.0
bystolic.com
12.25
viibryd.com
12.5
infedlocator.com
11.75
depakotehcp.com
17.0
depakote.com
16.5
taytulla.com
15.5
fetzima.com
11.25
Wave 2 site subtotal
166.25
Wave 2 total (+ foundation + overhead)
~219
PROGRAM ROLL-UP
Wave 1 (original six) — ~190 pd
Wave 2 (twelve new) — ~219 pd
Program grand total — ~409 pd
Range 355–465 pd · ≈ 71–93 person-weeks
Assumes the Wave-1 shared library is reused. Standalone (build the 12 shared blocks too): add ~36 pd.
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
12

## Slide 13
PHASING
Delivery Roadmap · Wave 1
A pod of 3 EDS engineers + tech lead + part-time PM/QA ≈ 11–14 calendar weeks (MLR in parallel).
WAVE 0
2–3 wks
Foundation
Design system, shared blocks, consent/analytics pattern, import pipeline. Validate on one pilot site.
WAVE 1
~4 wks
Lower-risk sites
lupron.com · lupronpedpro.com · armourthyroid.com — fetchable + modest interactivity.
WAVE 2
~4 wks
High-complexity
liletta.com · lilettahcp.com — most net-new interactive blocks (quiz, clinical data, forms).
WAVE 3
~2 wks
Discovery-led
hypothyroidhub.com — sequenced last; resolve scope/registration ambiguity first.
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
13

## Slide 14
PHASING
Delivery Roadmap · Wave 2
Wave 2 extends the same pod and lifecycle to 12 more sites ≈ 12–15 calendar weeks (MLR in parallel). Build order maximises reuse and defers the locator data dependency to last.
WAVE A
~3 wks
Quick wins · high-reuse
bystolic · viibryd · fetzima · xengelstent — small sites, all shared blocks; validate the reuse pattern.
WAVE B
~4 wks
Patient DTC + light interactivity
restasis · taytulla · myGlaucoma — savings flows, comparison/discussion tools, scored quiz.
WAVE C
~5 wks
HCP & multi-indication
viberzihcp · teflaro · depakote · depakotehcp — HCP gates, clinical/dosing tables, indication-selector; heaviest MLR.
WAVE D
~2 wks
Discovery-led
infedlocator — sequenced last; confirm the center-locator data source / API first.
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
14

## Slide 15
PLANNING CANDOR
Risks & Assumptions
Key risks & mitigations
⚠ MLR review = #1 schedule driver
Freeze content early; lock PRC codes; parallelise sign-off. 4 Wave-2 brands carry boxed warnings.
⚠ WAF-blocked + SPA sources
Discovery spikes first; re-baseline after — 3 Wave-1 + 10 of 12 Wave-2 sites not fetchable this pass.
⚠ hypothyroidhub scope unconfirmed
Scope spike before commit; could swing ±5 days.
⚠ Interactive blocks (a11y + CRM)
Early WCAG review; endpoint contracts up front.
⚠ Form endpoints (AbbVie/Veeva)
Confirm endpoint + INFeD locator data-source availability — external dependencies.
Key assumptions
One shared AbbVie design system; brands differ by tokens, not bespoke blocks.
Savings/copay enrollment stays on external AbbVie properties (link-out).
Authors / migration scripts handle bulk page authoring; engineering owns blocks + assembly.
MLR/regulatory review runs in parallel and does not block engineering.
Estimates re-baselined after Wave 0 and the discovery spikes (Wave-1 + Wave-2 non-fetchable sites).
AbbVie Pharma Portfolio → AEM Edge Delivery Services | Confidential – Client Proposal
15

## Slide 16
CASE STUDY • AGILENT • AI-AGENTIC DELIVERY
We migrated Agilent’s regulated product sites to Edge Delivery with a supervised fleet of specialist AI agents — each authoring, building, reviewing and shipping blocks end-to-end under human MLR sign-off.
6
Specialist agent fleet
Strategist, StyleForge, Blockwright, Sentinel, Composer & Pilot agents hand off each block from user story to PR — with code review and Playwright specs generated automatically.
70%
Faster block delivery
Agentic scaffolding, design-token mapping and automated test authoring cut net-new block lead time from days to hours across the migration.
100
PageSpeed at launch
The Pilot agent gates every page against a Lighthouse/PSI check — Core Web Vitals shipped green with no post-go-live remediation.
Result: 40+ pages and a reusable block library delivered by a human-supervised agent fleet — full MLR traceability and zero accessibility regressions. The same pipeline is ready to run for AbbVie.
Cognizant • Confidential client proposal

## Slide 17
WHY COGNIZANT
Proven EDS lifecycle, a reusable block library, and deep regulated-pharma experience — delivering performance, compliance and speed-to-author across the whole portfolio.
1
Scope & discovery spikes
Confirm hypothyroidhub + infedlocator scope; export WAF-blocked, SPA & non-fetchable content.
2
Foundation sprint (Wave 0)
Stand up design system, shared blocks & import pipeline on a pilot site.
3
Re-baseline & commit
Lock estimate and wave plan; agree MLR cadence and form/CRM dependencies.
Let’s start with a 2-week discovery sprint to lock scope across all 18 sites and validate the foundation.
Cognizant • Confidential client proposal